## Calcolatrice
Members
Name | In | # Tasks
Luca Brodo | LB | 23
Gordan Konevski | GK | 6
Wiktor Kochanek | WK | 9
Kaan Tuna | KT | 7
Vytaras Juraska | VJ | 6
Task Situation
|  |  | Situation | Total
|  |  | Completed | 26
|  |  | Work in Progrss | 2
|  |  | To-do | 1
|  |  | Total | 29
Tasks
[5 empty] | Task | Brief Description | Date | Status | Member | WIP
[5 empty] | Requirements Specification | Brief description of the requirements in bullet points |  | DONE | VJ
[5 empty] | Definition of the Context | Brief description of the context in which the car operates |  | DONE | WK
[5 empty] | Context Diagram | Definition of the context in a diagram |  | DONE | LB GK
[5 empty] | Block Diagram of the car | Composition of the car |  | DONE | LB, VJ
[5 empty] | SolidWork Model | First 3D model of the car |  | DONE | LB
[5 empty] | Requirements Diagram | Definition of the requirements in a diagram |  | DONE | LB
[5 empty] | Use Cases | Some use cases for the vehicle |  | DONE | LB, KT
[5 empty] | Water Wheels design | Design of wheels capable for water and all terrain |  | DONE | WK, VJ
[5 empty] | Simulation of the environment | Simulation in a host machine |  | DONE | LB
[5 empty] | Division of the vehicle in subsystems | Division of the vehicle in subsystems |  | DONE | KT
[5 empty] | Parametric Diagram | Specific Constraints of the seeking subsystem |  | DONE | KT, LB
[5 empty] | Specification of the vehicle dimension | Specification of the vehicle dimension according to the requirements |  | DONE | WK, KT, LB
[5 empty] | New model For the car | Design a new model in SolidWorks |  | DONE | LB,WK
[5 empty] | New Idea for the car exterior | Strictly related to the new model task |  | DONE | LB,WK
[5 empty] | Create dimensional Views | Create dimensional views of the model |  | DONE | WK
[5 empty] | Consider diffent aspects of the model | Different aspects like ergonomics and so on |  | DONE | WK,LB
[5 empty] | Define disciplines | Define disciplines for all subsystems |  | DONE | KT, LB
[5 empty] | Refine the subsystem | Refinement of the subsystem diagram |  | DONE | LB, KT
[5 empty] | Appropriate techniques | Uml and Algorithms for different parts |  | DONE | LB, GK,VJ | WIP
[5 empty] | Define a functional Model |  |  | DONE | LB, GK, KT, WK
[5 empty] | How to follow light | Define how the “Seeking ” subsystem works |  | DONE | LB, VJ
[5 empty] | Define Seeking subsistem | Uml, draft of algorithm for seeking subsystems |  | DONE | LB, VJ | WIP
[5 empty] | How does the robot maintain orientation | Decide how the model define orientation and map planning |  | WIP | GK, LB | WIP
[5 empty] | Map planning, path planning | Map planning and path planning ump and algorithm |  | WIP | GK, LB | WIP
[5 empty] | Define affordances and signifier | Different affordances and signifiers for the vehicle |  | DONE | LB,WK
[5 empty] | Conceptual Model | Definition of the conceptual model of the vehicle |  | DONE | LB
[5 empty] | Object Detection | Object Detection subsystem, UML |  | DONE | GK, LB
[5 empty] | Object Detection | Object Detection subsystem, First Library |  | DONE | LB
TO-DO
International Motor Company Ltd.